## Comm Plan Template
Project Plant Pals: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings.
Software and Equipment Vendor | Planning Check-In | Daily | Core Team: Administrative Coordinator | Every day at 10 a.m. | Phone Call | Go over the training manual in order to create an effective training plan for Office Green's employees | [link to training manual] | Revise the manual by the project manager
Human Resources | Planning Check-In | Daily | Core Team: Training Manager | Every day at 10 a.m. | In Person | Project planning assistance; provide support during the training session | [link to forum and virtual rooms and access to private messages] | Revise the planning of training and metodologies by project manager
Facilities | Training | One time | Core Team: Administrative Coordinator | March 1st all day | In Person | Reserve rooms, spaces, and equipment needed for employee training | [link to planning schedule and check list from activities completed on a spreadsheet] | Revise the schedule and completition by project manager
Print Shop | Planning Meeting | Weekly | Core Team: Administrative Coordinator | Monday at 9 a.m. | Phone Call | Coordinate on the printing and delivery of training manuals for employees | [link to schedule and check points] | Revise the schedule and completition by project manager
Office Green employees | Planning Meeting | One time | Core Team: Training Manager | March 1st all day | In Person | Communicate schedules, locations, and other necessary details to trainees | [link to schedule and check points] | Revise the schedule and completition by project manager
Office Green employees | Training | Daily | Core Team: HR Specialist & Training Manager | Every Day all day | In Person | Train employees to use the supply chain management software and equipment | [link to forum and virtual rooms and access to private messages] | Revise the schedule and completition by project manager
Office Green employees | Survey | One time | Core Team: HR Specialist & Training Manager | May, 30. All day to response. | Email (from individual address) | Post-training survey | [link to google forms] | Project manager evaluate and prepare a presentation with the results to manager and senior leaders and director of product, considering de PII protecting privacy of sensitive data
Your Manager | Planning Meeting | Weekly | Project Manager | Tuesday 10a.m. | In Person | Update on event planning, ask questions, and get feedback | [link to planning documentation on google drive] | Project manager presents results and receive feedback, decision could be make
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | Weekly | Project Manager | Wednesday 3p.m. | Email (from company address) | High-level information and general updates | [link to planning documentation on google drive] | Project manager presents results and receive feedback, decision could be make

## Comm Plan Template 2 (hidden)
Project Communication Plan
Project Title:
Project Manager:
Executive Sponsor:
Principal Stakeholder:
Date:
Deliverable Info (What) | Recipient(s) (Who) | Delivery Method(s) (How) | Schedule (When) | Who's Responsible? (Owner)
Project Information
Project Status
Agenda Minutes
Timeline Update
Project Updates Action Item Status
Project Risks

## Comm Plan Template 3 (hidden)
| Purpose | Medium | Frequency | Audience
Kickoff meeting
Project team meetings
Check-ins/ meeting recap
Project status meetings
UX design reviews