## Dashboard
Project Name: Plant Pals Program
Description: Provide low maintenance plants to the customers of the Office Green
Owner: Angélica Saraiva
Status: Draft
Key Docs | Link | Description
Project charter | https://docs.google.com/document/d/16N_vO8mA14sr7IiqXz6qbAOBRLwOa9QanMOHB3PKHeU/edit | obs: falta substituir os key docs pelos links colocando nomes nos arquivos e incluindo em apenas um shared folder e remover a coluna "links"
Statement of work | https://docs.google.com/document/d/18Q_ZL0IpAc2gRxp0kKEio9WAeptWXjvma3MFa7x88PY/edit
Risk management plan | https://docs.google.com/document/d/18QfdMXuT0LAjhEgKzyPx-djMKXe_ngZsqgNIqPaPkuw/edit
Schedule | Project Schedule
Budget | Budget
Communication plan | Communication Plan
Shared folder
RACI chart | https://docs.google.com/spreadsheets/d/18ZwObozanFIdInel1ZqhGeK87Tszd8gJ13IZDKcwftY/edit?pli=1#gid=479253282
WBS - Project tasks and milestones | https://docs.google.com/spreadsheets/d/11Hxg-IbMaVFPLC0V8r4lEClkCLItJLQcLJDTa7RIrMM/edit#gid=185434937
WBS - Work Breakdown Structure | https://docs.google.com/presentation/d/1xJYAARCKPSgaEtpdhvRPgKh1wmIPgbw5k3tb04re39E/edit#slide=id.p1

## Project Schedule
Gantt Chart
TITLE: Plant Pals Operations and Training Plan | [6 empty] | COMPANY NAME: |  |  |  |  | Office Green
PROJECT MANAGER: Angélica Saraiva | [6 empty] | CREATION DATE: |  |  |  |  | 02/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Establish a plant delivery and logistics plan | [5 empty] | 100% | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 10 | 0% | bar: MARCH M 100% to MARCH F 12
1.2 | Hire delivery drivers | Human Resources Specialist | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Calculate the delivery fees | Financial Analyst | 3/29 | 4/9 | 10 | 0% | bar: MARCH M 29 to APRIL F 9
2 | Select and install supply chain software and equipment
2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory Manager | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Supervise vendor installation of the fulfillment equipment | Fullfilment Director | 4/15 | 4/16 | 2 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Determine internal safety protocols for the equipment | Quality Assurance Tester | 4/19 | 4/30 | 10 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Develop and launch an employee training program
3.1 | Develop training sessions | Human Resources Specialist | 5/3 | 5/14 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Train employees to use the software and equipment | Training Manager | 5/17 | 5/28 | 10 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Monitor employee progress and improve training processes | Training Manager | 5/31 | 6/11 | 10 | 0% | bar: MAY M 31 to JUNE F 11

## Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/FINAL SPEND | UNDER/ OVER
[7 empty] | 62000 | 0 | 62000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | $/UNIT(S)
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Purchase delivery trucks | -- |  |  | 2 | 15000 |  | 30000 |  | -30000
Task 2: Source packaging materials | -- |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3: Pay delivery drivers | Delivery Drivers (2) | 160 | 15 |  |  |  | 2400 |  | -2400
[6 empty] | Total | 35400 | 0
Milestone 2: Select and install supply chain management software and equipment
Task 1: Source vendor (includes set up, installation, and deployment of systems) | -- |  |  |  |  | 15000 | 15000 |  | -15000
[6 empty] | Total | 15000 | 0
Milestone 3: Develop and launch an employee training program
Task 1: Develop training sessions | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2: Train employees to use the software and equipment | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
Task 3: Monitor employee progress and improve training processes | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
[6 empty] | Total | 8000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 62000 | 0

## Communication Plan
Project Plant Pals: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings.
Software and Equipment Vendor | Planning Check-In | Daily | Core Team: Administrative Coordinator | Every day at 10 a.m. | Phone Call | Go over the training manual in order to create an effective training plan for Office Green's employees | [link to training manual] | Revise the manual by the project manager
Human Resources | Planning Check-In | Daily | Core Team: Training Manager | Every day at 10 a.m. | In Person | Project planning assistance; provide support during the training session | [link to forum and virtual rooms and access to private messages] | Revise the planning of training and metodologies by project manager
Facilities | Training | One time | Core Team: Administrative Coordinator | March 1st all day | In Person | Reserve rooms, spaces, and equipment needed for employee training | [link to planning schedule and check list from activities completed on a spreadsheet] | Revise the schedule and completition by project manager
Print Shop | Planning Meeting | Weekly | Core Team: Administrative Coordinator | Monday at 9 a.m. | Phone Call | Coordinate on the printing and delivery of training manuals for employees | [link to schedule and check points] | Revise the schedule and completition by project manager
Office Green employees | Planning Meeting | One time | Core Team: Training Manager | March 1st all day | In Person | Communicate schedules, locations, and other necessary details to trainees | [link to schedule and check points] | Revise the schedule and completition by project manager
Office Green employees | Training | Daily | Core Team: HR Specialist & Training Manager | Every Day all day | In Person | Train employees to use the supply chain management software and equipment | [link to forum and virtual rooms and access to private messages] | Revise the schedule and completition by project manager
Office Green employees | Survey | One time | Core Team: HR Specialist & Training Manager | May, 30. All day to response. | Email (from individual address) | Post-training survey | [link to google forms] | Project manager evaluate and prepare a presentation with the results to manager and senior leaders and director of product, considering de PII protecting privacy of sensitive data
Your Manager | Planning Meeting | Weekly | Project Manager | Tuesday 10a.m. | In Person | Update on event planning, ask questions, and get feedback | [link to planning documentation on google drive] | Project manager presents results and receive feedback, decision could be make
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | Weekly | Project Manager | Wednesday 3p.m. | Email (from company address) | High-level information and general updates | [link to planning documentation on google drive] | Project manager presents results and receive feedback, decision could be make